My Proposal for Conducting MM Subjective Testing

- Source video sequences (e.g., 12-second AVI files containing VGA, CIF or QCIF) are collected & sent to ILG only.

- VQEG compiles a list of HRCs that can be created and by whom.

- Each organization that will perform subjective testing creates a proposed list of HRCs, This list will include more HRCs than will be needed, to allow designers to choose a more appropriate range of quality.

- The proposed lists of HRCs for each experiment are examined by the ILG for problems (e.g., one organization creating too many HRCs, overlap between experiments, using NTT guidelines).

- ILG & proponents will agree upon video sequences to be included in every experiment, as proposed by NTT (e.g., 5 SRC & 5 HRC, which would be 30 of 200 video sequences or 15%).

- Proponents submit their models.

- ILG select SRC sequences for each experiment & sends them only to the organization running that experiment.  ILG will send more SRCs than are required, to allow designers to choose a more appropriate range of quality.

- ILG creates a set of secret SRCs and secret HRCs.  The ILG conducts subjective experiments, and inserts these into proponents’ experiments.  Secret SRC and HRC must be included in the final experiment.

- The organization running each experiment will finalize their design based upon SRC & approved HRC list received from ILG.  The organization running the experiment will generate the HRCs, using the scenes that were sent to them in step 7, and finalize their experiment design.

- Each organization’s final test design and video scenes will be submitted to the ILG for approval before tests are conducted (i.e., after the extra sequences have been discarded).

- Each organization runs their test & submits results to the ILG.